## Overview
Category / metric | Pilot plan CNY | Full launch plan CNY | Pilot simulated actual CNY | Variance actual minus pilot CNY | Variance percent | Basis / exclusions
Guest services | 24000 | 24000 | 24600 | 600 | 2.5 | 30 guests; planned CNY 800 each, simulated actual CNY 820; includes food, tea, hosts and local transfers
Product development | 6000 | 24000 | 5500 | -500 | -8.33 | Assumed one-time preparation
Campaign | 8000 | 36000 | 7500 | -500 | -6.25 | Pilot plan 3000/3000/2000; simulated actual 2800/2900/1800
Operations / overhead | 7000 | 24000 | 6900 | -100 | -1.43 | Allocated labor/preparation overhead included; 40h is capacity estimate not extra billed labor
Contingency reserve / fallback spending | 5000 | 12000 | 2500 | -2500 | -50 | Reserve is within cap; only simulated amount used counts as outcome expense
TOTAL COST | 50000 | 120000 | 47000 | -3000 | -6 | All actuals fictional; no payments or supplier quotes
Revenue | 60000 | 60000 | 60000 | 0 | 0 | 30 guests x CNY 2000; no collections or bookings
Pre-tax operating result | 10000 | -60000 | 13000 | 3000 | 30 | Revenue minus total modeled expense; budget comparison treats entire reserve conservatively as cost
Operating margin percent | 16.67 | -100 | 21.67 |  |  | Percent, not CNY; exclusions below
Break-even guests | 22 | 80 | 19 |  |  | Guests, not CNY. ceil(fixed cost / (2000-variable cost)); pilot plan fixed 26000, full 96000, outcome 22400; full exceeds 30-guest capacity
Campaign cost per guest | 266.67 | 1200 | 250 | -16.67 | -6.25 | Campaign only, not total customer acquisition overhead
Assumptions and boundaries | [5 empty] | SIMULATION prepared 2026-09-27; scenario starts 2026-10-01; departure 2026-10-12. CNY only. Excludes flights, lodging, personal purchases, tax, financing and unrelated corporate costs. Figures illustrative, not market quotes. Static editable numeric cells, not live formulas.