## Overview
Task | Owner | Start | Finish | Days
SIMULATION evaluate options and decision | Wang, Sales lead; Chen, Director | 2026-10-01 | 2026-10-03 | 2
SIMULATION product, cost envelope and responsibilities | Zhao, Product lead; He, Operations lead | 2026-10-03 | 2026-10-06 | 3
SIMULATION campaign and invented guest funnel | Zhao, Product lead | 2026-10-06 | 2026-10-11 | 5
SIMULATION tabletop risk assessment and readiness checklist | He, Operations lead; Liu, People & culture lead | 2026-10-06 | 2026-10-08 | 2
SIMULATION no-external-action readiness gate | Chen, Director | 2026-10-11 | 2026-10-12 | 1
SIMULATION one-day experience for 30 fictional guests | He, Operations lead | 2026-10-12 | 2026-10-13 | 1
SIMULATION costs, forecast and outcome record | Deng, Finance lead; Chen, Director | 2026-10-13 | 2026-10-15 | 2
Local executive artifacts and reusable knowledge | Wang, Sales lead; Deng, Finance lead; Sun, IT & knowledge lead | 2026-10-15 | 2026-10-16 | 1